## Risk Overview
ID | Impact | Probability | Weight | Title | Description | Category | Comments | Actions | Reporter
1 | 4 | 3 | 12 | Unplanned resource unavailability | Due to critical deadline for launch of website in September, it is imperative that resources are available and knowledge stays in the project | Resources |  | 1 | SHH
2 | 2 | 3 | 6 | Migration Complexity | Failure to migrate properly from test environment to production environment can cause unstable behavior or in worst case downtime. | Technical Issue |  | 10 | SHH
3 | 4 | 2 | 8 | Performance Tests | Not meeting right level of performance will result in bad user experience causing bad-will and in worst case the users will not be able to use the website. | Technical Issue |  | 4 | SHH
4 | 4 | 5 | 20 | Load on servers when launching site | When launching the site it is expected that the hit rate will be extremely high comapred to normal day operation. The effect can be that the site will crash and the public will not be able to view the data causing bad-will. | Technical Issue |  | 4, 12, 13 | SHH
5 | 5 | 3 | 15 | Changing already agreed functionality | Change of agreed functionality can/will cause re-work or re-design resulting in work overhead and introducing added risk. With the strict deadline there isn't much time to do so and in worst case cause a failed deadline/launch | Commercial Issue Technical Issue | SHH: Probability lowered from 5 to 3. Impact remains the same. As part of mitigation measures COM/EEA are fully aware and will proactively try not to impose with new functionality or change already agreed functionality | 9, 14 | SHH
6 | 3 | 2 | 6 | Functinality that still needs to be specified | Functionality that is not specified or agreed to defer to a later stage can potentially introduce risk of delaying existing functionality | Technical Issue Planning |  |  | SHH
7 | 3 | 5 | 15 | Availability of valid data from Member States in time | It is important to receive valid data in order to populate the databases and thus verify the data model the site is build upon. | Commercial Issue Technical Issue |  | 3 | SHH
8 | 3 | 5 | 15 | Requiring functionality that is out of scope/contract | The requirements outlined in the Service Contract are specified at a very high level which introduces the possibility of Introducing new requirements, having different expectations and common understanding. | Commercial Issue |  | 7, 8 | SHH
9 | 2 | 5 | 10 | Member States not conforming with schemas / data model | If member states do not conform with the schemas, eg. claiming confidentiality for all fields etc., the result will be that the data will not comply with the data model or the databases will not be populated. Altering the data model to adapt special rules | Commercial Issue Technical Issue Processes |  | 5 | SHH
10 | 1 | 5 | 5 | Multiple sources for version control and issue tracking | Having more than one source for version control and issue tracking can create confusion and redundancy of information. In worst case valuable information can be lost. Today two repositories exists for version control and issue tracking: https://svn.eionet | Processes |  | 11 | SHH
11 | 2 | 3 | 6 | CMS support to COM | COM requires CMS support |  |  |  | KTH
12 | 2 | 3 | 6 | Integration of info pages from separate contract | The info pages concerning pollutant, activity and waste are created by another contractor. The integration of these pages might be more difficult than expected. |  |  | 2 | HES
13 | 2 | 2 | 4 | Text lengths for static text content exeeding expectation | Text content delievered by COM/EEA may not directly fit into the static pages, because the texts are too long. | Technical |  | 6 | SHH
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
Impact levels
|  |  |  | 5 | VERY HIGH: >20% Work increase/Slippage - Project end item is effectively useless, Project end item is effectively unusable
|  |  |  | 4 | HIGH: 10-20% Work increase/Slippage - Scope reduction unacceptable to client, Quality reduction unacceptable to the client
|  |  |  | 3 | MODERATE: 5-10% Work increase/Slippage - Major areas of scope are affected, Quality reduction requires client approval
|  |  |  | 2 | LOW: < 5% Work increase
|  |  |  | 1 | Project economy, quality or functionality is affected negatively
Probability levels
|  |  |  | 5 | Very Likely (More than 75%)
|  |  |  | 4 | Likely (Between 50% and 75%)
|  |  |  | 3 | Somewhat likely (20% - 50%)
|  |  |  | 2 | Unlikely (10% - 20%)
|  |  |  | 1 | Very Unlikely (less than 10%)

## Mitigation and Contingency Act
# | Risk No. | Propability | Weight | Title | Action | Resp | Type | Status | Comments
1 | 1 | 3 | 12 | Unplanned resource unavailability | Ensure knowledge sharing and available critical mass ressources | Atkins | Mit | In progress
2 | 12 | 3 | 6 | Integration of info pages from separate contract | Get proof of concept ASAP | COM | Mit | Waiting
3 | 7 | 5 | 15 | Availability of valid data from Member States in time | There will be three windows for upload. 15 September is the latest. Request MS to leave confidential fields blank in order not to use extra effort to analyse "garbage" data. | COM | Mit | Waiting
4 | 4 | 5 | 20 | Load on servers when launching site | [Risk #3 & #4] Define and implement proper caching. | EEA/Atkins | Cont | Not started
5 | 9 | 5 | 10 | Member States not conforming with schemas / data model | Data load procedures will leave out facilities for which delivered data does not conform with datamodel, rather than trying to analyse and make 'sense' out of garbage data. | Atkins | Cont | Not started
6 | 13 | 2 | 4 | Text lengths for static text content exeeding expectation | COM is in instructed to keep explanatory text bodies for static pages shorter than half a page (writing in Word; size 10) | COM | Mit | In progress
7 | 8 | 5 | 15 | Requiring functionality that is out of scope/contract | COM is willing to accept it when Atkins flags a functionality/activity as out of scope. | COM | Mit | In progress
8 | 8 | 5 | 15 | Requiring functionality that is out of scope/contract | Atkins must early and clearly indicate to COM when a requested functionality/activity seems out of scope. | Atkins | Mit | In progress
9 | 5 | 3 | 15 | Changing already agreed functionality | Decisions from all correspondences are systematically written down | Atkins/COM | Mit | In progress
10 | 2 | 3 | 6 | Migration Complexity | a) Atkins/EEA will make an early test software installation at EEA's site. b) Atkins will setup an internal integration server that runs the latest functionality drop that is ready to migrate to EEA's site. c) Atkins maintains an installation manual for all involved software components. | Atkins/EEA | Mit | Starting mid-april
11 | 10 | 5 | 5 | Multiple sources for version control and issue tracking | Prepare detailed instructions using the two systems. | Atkins | Mit | Starting mid-april
12 | 4 | 5 | 20 | Load on servers when launching site | Redirect incoming users to a max load page in case server overload | Atkins | Mit | Not started
13 | 4 | 5 | 20 | Load on servers when launching site | Reduce functionality in launch period. | Atkins | Cont | Not started
14 | 5 | 3 | 15 | Changing already agreed functionality | COM/EEA are fully aware and will proactively try not to impose with new functionality or change already agreed functionality | COM | Mit | In progress
15 |  | #N/A | #N/A | #N/A