## Hoja1
EPRTRandLCP | Responsible | Done | Description of the task | Observations
REPORNET INFRASTRUCTURE | EEA
Obligation registered in EIONET |  |  | Examples of other obligations LCP: http://rod.eionet.europa.eu/obligations/9 EPRTR: http://rod.eionet.europa.eu/obligations/538 WFD: http://rod.eionet.europa.eu/obligations/715
Create the roles for the National Coordinators at EIONET |  |  | Examples LCP: ?¿ EPRTR: ?¿ WFD: http://rod.eionet.europa.eu/contacts?roleId=extranet-wfd-data
National Coordinators registered in their roles at EIONET
Create the roles for the Data Reporters at EIONET
Data Reporters registered in their roles at EIONET
Create a Help page with the specifications of the reporting |  |  | Examples of other helps LPC: http://cdr.eionet.europa.eu/help/lcp EPRTR: http://cdr.eionet.europa.eu/help/eprtr WFD: http://cdr.eionet.europa.eu/help/WFD | *** It is very different the documentation of the three projects, so we need to know which type of guidelines document is required
Helpdesk for EPRTRandLCP
Collections/Envelopes structure by country under the obligation |  |  | First version in test: http://cdrtest.eionet.europa.eu/at/eu
Reporting workflow at Reportnet
REPORTNET TOOLS | Bilbomatica
UML |  |  | https://svn.eionet.europa.eu/repositories/EPRTR/E-PRTR%20and%20LCP/TASK1/
Schemas |  |  | http://dd.eionet.europa.eu/schemaset/LCPandPRTR/view https://svn.eionet.europa.eu/repositories/EPRTR/E-PRTR%20and%20LCP/TASK2/
Access and SQL databases design |  |  | https://svn.eionet.europa.eu/repositories/EPRTR/E-PRTR%20and%20LCP/TASK4/
QA: Within schema checks and added into Reportnet as FME process |  |  | Example of WFD http://fme.discomap.eea.europa.eu/fmeserver/repositories#/repo/WFD https://svn.eionet.europa.eu/repositories/Reportnet/Dataflows/WaterFrameworkDirective/WFD2016/QA-QC/Project/trunk/QAQC/XQuery/ | *** Bilbomatica has the QA definitions and code uploaded to the following SVN: https://svn.eionet.europa.eu/repositories/EPRTR/E-PRTR%20and%20LCP/TASK3/ **** Bilbomatica has created the FME repository: http://fme.discomap.eea.europa.eu/fmeserver/repositories#/repo/E-PRTRandLCP
Conversion tool (MDB to XML)
EU compilation process (XML) |  |  | http://fme.discomap.eea.europa.eu/fmeserver/repositories#/repo/E-PRTRandLCP
DATABASES
Current SQL databases to get real data | EEA |  | LCP: ?¿ EPRTR: Ok | *** Because of we worked on EPRTR years ago, we have checked the production sql server (TETRASQL) and we have seen three databases: EPRTRWeb, EPRTEPublic and EPRTRMaster. But we haven't seen the LCP database. We don't know how is the LCP data managed after the reporting by webforms.
MDB with real data | Bilbomatica |  | With the links provided by Rolf-Jan we can access to the MDBs, and we will try to fill the new designed MDB with this current data
Integration with Central Registry | EEA |  | We have no information abour Central Register | *** We decided in summer (in the FME proposal presentation) that we will create two primary ID (on for Plants and one for Facilities). These two Ids will be managed by the Central Register. We don't have more information, so we cannot write the integration documentation without the information of the destination structure
Data for the validations with other years | EEA/Bilbomatica |  | There are several QAs that check data from other years. We need to know how are these validations implemented now in LCP. | *** These validations are in the excel file (in yellow): https://svn.eionet.europa.eu/repositories/EPRTR/E-PRTR%20and%20LCP/TASK3/QA_QC/ *** Bilbomatica could implement an FME process for these QAs, but we will need data for the last three years.
WORKSHOP | DG
Library repository |  |  | Example of WFD: http://forum.eionet.europa.eu/x_wise-reporting/library/water-framework-directive-library/2015.11.12-water-framework-directive-reporting-workshop
Logistics